## Test Cases
Movie Ticket Management System — Test Cases
Agile Software Project Management Simulation — Full Test Case List
Test ID | Test Type | Feature | Objective | Input | Expected Output | Actual Output | Status | Tested By
TC-001 | Unit | Registration | Validate a new customer can register with valid details | Valid name, email, phone, password | Account created; success message; redirected to login | Account created successfully; confirmation message shown | Pass | Dikpal Pandey
TC-002 | Unit | Registration | Validate duplicate email is rejected | Email: aarav@test.com (existing) | 'Email already registered' error shown | Error message displayed as expected | Pass | Dikpal Pandey
TC-003 | Unit | Login | Validate login succeeds with correct credentials | Email: aarav@test.com; Password: Pass@123 | User authenticated; redirected to movie listing | Login successful; movie list displayed | Pass | Dikpal Pandey
TC-004 | Unit | Login | Validate login fails with incorrect password | Email: aarav@test.com; Password: wrongpass | 'Invalid credentials' error shown | Error message displayed as expected | Pass | Dikpal Pandey
TC-005 | Unit | Browse Movies | Validate movies can be filtered by genre | Filter: Genre = Action | Only 'Action' movies displayed | Filtered list showed only Action titles | Pass | Dikpal Pandey
TC-006 | Unit | Showtimes | Validate available showtimes are listed for a movie | Movie: 'Interstellar Voyage' | All active showtimes listed with date/time | Showtimes list displayed correctly | Pass | Rojit Malla
TC-007 | Unit | Seat Selection | Validate an already-booked seat cannot be reselected | Seat C5 (status = booked) | Seat C5 disabled/unselectable; selection blocked | Seat C5 still selectable and allowed into cart (validation gap) | Fail | Rojit Malla
TC-008 | Unit | Pricing | Validate total price is calculated for multiple seats | Seats: A1, A2, A3 @ $10.00 each | Total displayed = $30.00 | Total displayed correctly as $30.00 | Pass | Rojit Malla
TC-009 | Integration | Registration + Database | Verify new user record is persisted correctly | Email: priya@test.com | New row exists in Users table with matching details | User row created and matched submitted data | Pass | Dikpal Pandey
TC-010 | Integration | Login + Session | Verify session token persists across pages | Email: priya@test.com | Session remains active across navigation | Session persisted correctly across navigation | Pass | Dikpal Pandey
TC-011 | Integration | Seat Selection + Booking | Verify selected seats are locked during checkout | Seat B4; two customers, 5-min lock window | Seat B4 locked for second customer during checkout | Seat lock enforced as expected | Pass | Rojit Malla
TC-012 | Integration | Booking + Payment Gateway | Verify booking invokes payment gateway with correct amount | Order amount: $30.00; Method: Credit Card | Gateway receives correct amount and booking reference | Payment gateway received correct amount and reference ID | Pass | Rojit Malla
TC-013 | Integration | Payment + Booking Status | Verify booking rolls back when payment fails | Card: declined test card | Payment fails; booking cancelled; seat returns to available | Payment failed, but seat remained 'pending' and was not released | Fail | Rojit Malla
TC-014 | Integration | Booking + Notification | Verify confirmation is triggered after payment | Booking ID: BKG-1042 | Confirmation queued/sent with booking details and e-ticket | Confirmation sent with correct booking details | Pass | Rojit Malla
TC-015 | System | End-to-End Booking | Verify a customer can complete a full booking | Movie: 'Interstellar Voyage'; Seats: D1, D2 | Booking confirmed; e-ticket generated and shown | Full booking flow completed; e-ticket generated successfully | Pass | Rojit Malla
TC-016 | System | Cancel Booking | Verify cancelling releases the seat back to inventory | Booking ID: BKG-1050; Seat: E6 | Seat E6 becomes available immediately | Booking cancelled, but seat E6 still showed 'booked' for several minutes | Fail | Rojit Malla
TC-017 | System | Admin – Add Movie & Showtime | Verify admin can add a movie and schedule a showtime | Movie: 'The Last Reel'; Theater: Hall 3; Time: 7:00 PM | New movie and showtime appear in customer catalog | New movie and showtime appeared correctly for customers | Pass | Dikpal Pandey
TC-018 | System | Concurrent Booking Prevention | Verify two customers cannot book the same seat | Seat: F2; Showtime: 8:30 PM | Only one booking succeeds; second gets 'seat unavailable' | Only one booking succeeded; second attempt blocked as expected | Pass | Rojit Malla
TC-019 | System | Booking History | Verify a customer can view past and upcoming bookings | Customer: priya@test.com | All bookings listed with correct status and details | Booking history displayed accurately | Pass | Dikpal Pandey
TC-020 | System | Payment Failure Handling | Verify system handles a declined payment gracefully | Card: declined test card | Clear error shown; customer returned to payment step | Error message shown; customer returned to payment step | Pass | Rojit Malla
TC-021 | UAT | Registration & Login | Confirm a first-time customer can register and log in | New user: 'Test User' | Registration and login completed within a few steps | User completed the flow smoothly and understood each step | Pass | Dikpal Pandey
TC-022 | UAT | Browse & Showtimes | Confirm a customer can find a movie and its showtimes | Search term: 'Interstellar' | Movie and showtimes located quickly using visible navigation | Customer found the movie and showtimes without guidance | Pass | Dikpal Pandey
TC-023 | UAT | Seat Selection & Booking | Confirm a customer can select seats and book without confusion | Seats: G1, G2 | Seat selection and payment completed confidently | Booking completed with minor hesitation over price breakdown | Pass | Rojit Malla
TC-024 | UAT | Booking Confirmation Clarity | Confirm the confirmation clearly shows seat numbers | Booking ID: BKG-1061; Seats: G1, G2 | Confirmation clearly lists movie, showtime, theater, and seat numbers | Confirmation showed booking ID and time, but seat numbers were not clearly visible | Fail | Rojit Malla
TC-025 | UAT | Admin Usability | Confirm an administrator can manage movies and showtimes easily | Movie: 'The Last Reel' | Management tasks completed using clearly labeled controls | Administrator completed tasks efficiently with no issues | Pass | Dikpal Pandey

## Summary
Movie Ticket Management System — Testing Summary
Agile Software Project Management Simulation
Test Type | Total Cases | Passed | Failed
Unit | 8 | 7 | 1
Integration | 6 | 5 | 1
System | 6 | 5 | 1
UAT | 5 | 4 | 1
Total | 25 | 21 | 4
Pass Rate: | 84%
Linked Defect Log
Defect ID | Severity | Issue | Found In
DEF-01 | High | Duplicate seat validation allowed booking of an already-reserved seat. | TC-007
DEF-02 | Medium | Cancelled booking did not immediately release the seat back to inventory. | TC-016
DEF-03 | High | Payment failure did not roll back the pending seat reservation. | TC-013
DEF-04 | Medium | Booking confirmation did not clearly display the selected seat numbers. | TC-024